## Sheet1
Country | Project / Contract | Approval | Approval Holder | Species of National Significance (AUS/NZ) | IUCN Listed Classification | Risk (Potential / Actual) | Mitigation | Status
New Zealand | Milford Road Alliance (NZ) Customer: Waka Kotahi | Liaison with Department of Conservation and Wildlife Permit | Downer | Southern lesser short-tailed bat (Mystacina tuberculata tuberculata) | Not Listed | Potential - Removal of habitat due to required tree felling | Avoid and Minimise | Completed
New Zealand | Marshland Bridge and Roading Customer: Christchurch City Council | Liaison with Department of Conservation NIWA, Fish and Game and Wildlife Permit (For lizards) | Downer | Swamp Nettle (Urtica perconfusa) | Not Listed | Potential - Removal of habitat due to vegetation removal and bank realignment as well as culvert extension in drain | Avoid, Minimise and Relocate Potential impacts managed through an approved Threatened Species Management Plan. | Completed
|  |  |  | Common Grass Skink (Oligosoma polychroma) | LC Least Concern
|  |  |  | McCann's skink (Oligosoma maccanni) | LC Least Concern
|  |  |  | Lamprey (Geotria australis) | DD Data Deficient
|  |  |  | Longfin Eel (Anguilla dieffenbachii) | EN Endangered
|  |  |  | Shortfin Eels (Anguilla australis) | NT Near Threatened
New Zealand | Christchurch Southern Motorway (CSM2) Customer: Waka Kotahi | Liaison with Department of Conservation and Wildlife Permit | Downer | Common Grass Skink (Oligosoma polychroma) | LC Least Concern | Potential - Removal of habitat during vegetation/ shelterbelt removal. | Avoid, Minimise and Relocate | Completed
New Zealand | Turitea Wind Farm Customer: Mercury | Resource consent conditions | Downer | Snails (Powelliphanta) | NT Near Threatened | Potential - Removal of habitat | Avoid, Minimise and Relocate | In progress
New Zealand | America’s Cup AC36 Village/ Wharf Customer: Auckland Council | Resource consent conditions | Downer | Red Billed Gull (Larus novaehollandiae scopulinus) | Not Listed | Actual - Relocation required | Avoid, Minimise and Relocation of colony of 400 individuals | Completed
Australia | High Capacity Metro Trains Depot (HCMT) East Pakenham Depot Customer: Public Transport Victoria | EPBC Approval | Customer | Southern Brown Bandicoot (Isoodon obesulus) | LC Least Concern | Potential - Habitat disturbance | Avoid, Minimise and Offsets Potential impacts managed through an approved Threatened Species Management Plan. | Operational
|  |  |  | Growling Grass Frog (Litoria raniformis) | EN Endangered
|  |  |  | Matted flax-lily (Dianella amoena) | Not Listed
|  |  |  | Maroon leek-orchid (Prasophyllum frenchii) | Not Listed
|  |  |  | Dwarf galaxias (Galaxiella pusilla) | EN Endangered
Australia | HCMT Calder Park - Light Stabling Facility Customer: Public Transport Victoria | EPBC Approval | Customer | Growling Grass Frog (Litoria raniformis) | EN Endangered | Potential - Due to habitat disturbance | Avoid and Minimise Interaction with Growling Grass Frog managed using a specific species management plan including frog exclusion fencing. | In progress
Australia | Western Port Highway upgrade Customer: Major Roads Projects Victoria | Victorian State Approval | Customer | Southern Brown Bandicoot (Isoodon obesulus) | LC Least Concern | Potential - Due to habitat disturbance | Restore Four fauna culverts were constructed to protect and strengthen the movement corridor and habitat range. | In progress
Australia | Warrnambool Line Upgrade Customer: Rail Projects Victoria | Victorian State Approval | Customer | Growling Grass Frog (Litoria raniformis) | EN Endangered | Potential - Due ot habitat disturbance | Avoid, Minimise and Restore Interaction with Growling Grass Frog managed using a specific species management plan. A fauna culvert has been constructed to enhance connectivity and habitat range. | In progress
Australia | O’Herns Road Customer: Main Roads Project Victoria | EPBC Approval | Customer | Growling Grass Frog (Litoria raniformis) | EN Endangered | Potential - Due to habitat disturbance | Avoid, Minimise and Offsets Removal of habitat reduced as far as possible through design, including installation of a Growling Grass Frog Culvert. Construction impacts through species specific management plans. | Completed
|  |  |  | Golden Sun Moth (Synemon plana) | Not Listed
Australia | P0008 RAAF Base Williamtown Customer: Department of Defence | EPBC Approval | Customer | Regent honeyeater (Anthochaera phrygia) | CR Crtiically Endangered | Potential | Avoid No flora / fauna removal is required or approved for this project. No flora or fauna is expected to be impacted from the construction zones / proximity to works. Impact mitigated through exclusion zones. Potential impacts managed through an approved Threatened Species Management Plan. | In progress
|  |  |  | Swift parrot (Lathamus discolour) | CR Crtiically Endangered
|  |  |  | Australian bittern (Botaurus poiciloptilus) | EN Endangered
|  |  |  | Australian painted snipe (Rostratula australis) | EN Endangered
|  |  |  | Koala (Phascolarctos cinereus) | VU Vulnerable
|  |  |  | Long-nosed potoroo (Potorous tridactylus) | NT Near Threatened
|  |  |  | Grey-headed flying fox (Pteropus poliocephalus) | VU Vulnerable
|  |  |  | White-throated needletail (Hirundapus caudacutus) | LC Least Concern
|  |  |  | New Holland mouse (Pseudomys novaehollandiae) | VU Vulnerable
|  |  |  | Dwarf Kerrawang (Commersonia prostrata) | Not Listed
|  |  |  | Earp’s red gum (Eucalyptus parramattensis var. decadens) | Not Listed
Australia | Bango Wind Farm Customer: CWP Renewables | EPBC Approval | Customer | Golden Sun Moth (Synemon plana) | Not Listed | Potential - Due to disturbance of habitat during construction phase clearing works. Clearing potential habitats or generating excessive noise in close proximity to potential habitats during breeding seasons. | Avoid and Minimise Potential impacts managed through an approved Threatened Species Management Plan. | In progress
|  |  |  | Superb Parrot (Polytelis swainsonii) | LC Least Concern
|  |  |  | Derived Native Grassland ecological community | Not Listed
|  |  |  | White Box-Yellow Box-Blakely’s Red Gum Grassy Woodland ecological community | Not Listed
Australia | Thornlie Cockburn Customer: Public Transport Authority of Western Australia / Office of Major Transport Infrastructure Delivery | EPBC Approval | Customer | Carnaby’s Black Cockatoo (Calyptorhynchus latirostris) | EN Endangered | Potential - Due to vegetation/ habitat disturbance | Avoid and Minimise Potential impacts managed through an approved Threatened Species Management Plan. | In progress
|  |  |  | Baudin’s Black Cockatoo (Calyptorhynchus baudinii) | EN Endangered
|  |  |  | Red-tailed Black Cockatoo (Calyptorhynchus banksii) | LC Least Concern
|  |  |  | King Spider-orchid (Caladenia procera) | Not Listed
|  |  |  | Banksia Woodlands ecological community | Not Listed
Australia | Yanchep Rail Extension Parts 1 and 2 Customer: Public Transport Authority of Western Australia / Office of Major Transport Infrastructure Delivery | EPBC Approval | Customer | Carnaby’s Black Cockatoo (Calyptorhynchus latirostris) | EN Endangered | Potential - Due to vegetation/ habitat disturbance | Avoid and Minimise Potential impacts managed through an approved Threatened Species Management Plan. | In progress
|  |  |  | Western Quoll (Dasyurus geoffroii) | NT Near Threatened
|  |  |  | Banksia Woodlands of the Swan Coastal Plain ecological community | Not Listed
Australia | Project EnergyConnect (SA/NSW Interconnector) Customer: ElectraNet | EPBC Approval | Customer | Black Eared Miner (Manorina melanotis) | EN Endangered | Potential - Due to vegetation/ habitat disturbance | Avoid and Minimise Potential impacts managed through an approved Threatened Species Management Plan. | In progress
|  |  |  | Regent Parrot (eastern subspecies) (Polytelis anthopeplus monarchoides) | LC Least Concern
Australia | Eyre Peninsula Link Customer: ElectraNet | EPBC Approval | Customer | Malleefowl (Leipoa ocellata) | VU Vulnerable | Potential - Due to vegetation/ habitat disturbance | Avoid and Minimise Potential impacts managed through an approved Threatened Species Management Plan. | In progress
|  |  |  | Sandhill dunnart (Sminthopsis psammophila) | VU Vulnerable
|  |  |  | Southern emu-wren (Stipiturus malachurus parimeda) | LC Least Concern
|  |  |  | Western grasswren (Amytornis textilis myall) | LC Least Concern
|  |  |  | Jumping-jack wattle (Acacia enterocarpa) | Not Listed
|  |  |  | Green-comb spider-orchid (Caladenia tensa) | Not Listed
|  |  |  | Silver daisy-bush (Olearia pannosa ssp. pannosa) | Not Listed
|  |  |  | Tufted bush-pea (Pultenaea trichophylla) | Not Listed
|  |  |  | Eyre Peninsula Blue Gum (Eucalyptus petiolaris) Woodland ecological community | Not Listed